## Board
Team 23 — Employee Management System · Scrum board
Iteration 2 (post-demo weekly rota). Filter by Status or Epic; change a card by editing its Status cell (dropdown). Every card points at the file or test that proves it.
Status | Epic | Card | Owner | Evidence / notes
Done | Employees (FR01–FR05) | Add / edit / delete employee records | Dylan | app/views.py, repositories.py; FR01–FR03
Done | Employees (FR01–FR05) | Field-level validation + friendly error page | Dylan | htmlpages.validate_employee; FR11
Done | Employees (FR01–FR05) | Delete cascades to all rota rows | Morty | FK ON DELETE CASCADE; TC-19; test_delete_also_removes_the_linked_shift
Done | Employees (FR01–FR05) | Search by name / address / phone / e-mail | Dylan | repositories.search_employees; FR04
Done | Employees (FR01–FR05) | Wage-range + weekly-shift filters and sorting | Dylan | search_employees + the filter bar on the home page; FR12
Done | Employees (FR01–FR05) | Employee table with weekly shift summary | Jensen | templates/partials/employee_table.html; FR05
Done | Security & roles (FR09/FR10, NFR02) | Role-based access control for the three roles | Morty | route role lists + dispatcher; FR09/FR10, NFR02
Done | Security & roles (FR09/FR10, NFR02) | CSRF protection on every form | Morty | per-session token, refused with 400; tests
Done | Security & roles (FR09/FR10, NFR02) | PBKDF2 passwords + server-side sessions | Morty | app/security.py; NFR02
Done | Security & roles (FR09/FR10, NFR02) | Login lands on Home, then branches by role | Dylan | views.login; URS section 7
Done | Weekly rota (FR06–FR08) | Dated rota rows (employee + date + shift) | Morty | shifts table + unique index; TC-31/32
Done | Weekly rota (FR06–FR08) | Several shifts on the same day | Spring | unique(employee_id, work_date, shift_name); TC-32/55
Done | Weekly rota (FR06–FR08) | Week navigation ?week= (prev / next / this) | Spring | _week_context(); all weekly pages; TC-52/53
Done | Weekly rota (FR06–FR08) | Legacy database upgraded and reseeded | Morty | initialize() + _reseed_demo_rota(); SchemaMigrationTests; TC-57
Done | Weekly rota (FR06–FR08) | Current-week demonstration rota seed | Spring | database.seed / _demo_rota; one employee with an empty week
Done | Weekly rota (FR06–FR08) | Rota panel on the detail page (Supervisor only) | Spring | employee_detail.html; FR10; HR has no panel
Done | Role views (FR07/FR08) | Employee weekly timetable (shift × day grid) | Jensen | templates/my_shifts.html; FR07; TC-41/55
Done | Role views (FR07/FR08) | Supervisor roster grouped by day | Spring | templates/store_shifts.html + day_roster(); FR08; TC-38
Done | Role views (FR07/FR08) | HR roster grouped by employee + filters | Spring | store_shifts.html + employee_roster(); FR08/FR12; TC-54
Done | Role views (FR07/FR08) | Home = searchable Employee overview + actions | Jensen | templates/home_staff.html; FR05; /employees removed
Done | Role views (FR07/FR08) | Employee home: own details + this week's shifts | Jensen | templates/home_employee.html
Done | Role views (FR07/FR08) | Employees-per-shift distribution table | Jensen | employee_counts_per_shift(); shift-table on the home page
Done | Statistics (FR13) | Weekly KPIs (employees / shifts / unassigned / wage) | Jensen | home_staff.html; FR13; TC-58
Done | Statistics (FR13) | Weekly statistics page | Jensen | templates/statistics.html; FR13
Done | Quality (NFR01/03/05) | 137 automated tests | Morty | tests/; Ran 137 tests — OK
Done | Quality (NFR01/03/05) | 40 end-to-end HTTP checks | Morty | docs/verify_running_app.py
Done | Quality (NFR01/03/05) | 7 persistence checks | Morty | docs/verify_persistence.py; NFR03
Done | Quality (NFR01/03/05) | Performance check with 400+ employees | Morty | tests/test_nonfunctional.py; NFR01
Done | Documentation | URS 1.3 (weekly rota + three role views) | Morty | docs/URS-Team23-1.3.docx
Done | Documentation | Test Plan 1.1 (60 cases + traceability) | Morty | docs/Test Plan-Team 23.docx
Done | Documentation | Code Guide (code walkthrough) | Jensen | docs/Code Guide-Team 23.docx
Done | Documentation | README updated (rota, upgrade path, 137 tests) | Dylan | README.md
Done | Documentation | Demo script + Q&A preparation | Spring | docs/答辩演示脚本.md, docs/答辩准备包.md
Done | Documentation | Verification scripts updated for weekly rota | Morty | docs/verify_running_app.py, docs/verify_persistence.py
Done | Delivery | Push to GitHub (master @ b0c6f7c) | All | origin/master synced, working tree clean
Busy | Delivery | Copy URS 1.3 / Test Plan / Code Guide to the course folder | Dylan | manual copy; the sandbox cannot write outside the workspace
Busy | Delivery | Demo rehearsal with the three accounts | All | run app.py, walk docs/答辩演示脚本.md end to end
To Do | Documentation | Update Acceptance Q&A (EN + bilingual) | Spring | Q20 still says one shift per employee; update counts and overview wording
To Do | Delivery | Confirm the other-group test report is submitted | Morty | a deliverable listed in the Project Plan
To Do | Delivery | Defence slides (finish / confirm) | Jensen | follow the demo storyline: rota → views → docs → tests
To Do | Delivery | Optional: tag release v1.1 + CHANGELOG | Dylan | after submission; tag the pushed commit

## Board View
Board view — epics × status
Epic | To Do | Busy | Done
Employees (FR01–FR05) |  |  | • Add / edit / delete employee records • Field-level validation + friendly error page • Delete cascades to all rota rows • Search by name / address / phone / e-mail • Wage-range + weekly-shift filters and sorting • Employee table with weekly shift summary
Security & roles (FR09/FR10, NFR02) |  |  | • Role-based access control for the three roles • CSRF protection on every form • PBKDF2 passwords + server-side sessions • Login lands on Home, then branches by role
Weekly rota (FR06–FR08) |  |  | • Dated rota rows (employee + date + shift) • Several shifts on the same day • Week navigation ?week= (prev / next / this) • Legacy database upgraded and reseeded • Current-week demonstration rota seed • Rota panel on the detail page (Supervisor only)
Role views (FR07/FR08) |  |  | • Employee weekly timetable (shift × day grid) • Supervisor roster grouped by day • HR roster grouped by employee + filters • Home = searchable Employee overview + actions • Employee home: own details + this week's shifts • Employees-per-shift distribution table
Statistics (FR13) |  |  | • Weekly KPIs (employees / shifts / unassigned / wage) • Weekly statistics page
Quality (NFR01/03/05) |  |  | • 137 automated tests • 40 end-to-end HTTP checks • 7 persistence checks • Performance check with 400+ employees
Documentation |  |  | • URS 1.3 (weekly rota + three role views) • Test Plan 1.1 (60 cases + traceability) • Code Guide (code walkthrough) • README updated (rota, upgrade path, 137 tests) • Demo script + Q&A preparation • Verification scripts updated for weekly rota
Delivery | • Confirm the other-group test report is submitted • Defence slides (finish / confirm) • Optional: tag release v1.1 + CHANGELOG | • Copy URS 1.3 / Test Plan / Code Guide to the course folder • Demo rehearsal with the three accounts | • Push to GitHub (master @ b0c6f7c)

## Summary
Project snapshot
Repository | https://github.com/JJC-Dylan/team23-ems
Branch / HEAD | master @ b0c6f7c (pushed, tree clean)
Commits | cc15a6a initial · adf844c weekly rota · b0c6f7c docs
Iteration | 2 — post-demonstration weekly rota (2026-10-18 → 2026-10-21)
Functional requirements | FR01–FR13 delivered; FR14–FR18 Won't-have
Non-functional requirements | NFR01–NFR06 met
Automated tests | 137 pass (Python 3.10.1)
End-to-end checks | 40 pass (docs/verify_running_app.py)
Persistence checks | 7 pass (docs/verify_persistence.py)
Documents | URS 1.3 · Test Plan 1.1 · Code Guide · README
Owner legend | Dylan = employee module · Spring = rota · Morty = database · Jensen = frontend (suggested)
Automated test inventory
Test module | Cases | Level | Result
tests/test_auth_and_access.py | 20 | Integration | Pass
tests/test_employees.py | 34 | Integration | Pass
tests/test_shifts.py | 58 | Integration (weekly rota, migration) | Pass
tests/test_nonfunctional.py | 7 | Non-functional | Pass
tests/test_templateengine.py | 10 | Unit | Pass
tests/test_live_server.py | 8 | System / E2E | Pass
TOTAL automated | 137 | — | Pass
End-to-end HTTP checks | 40 pass
Persistence checks | 7 pass
Website status | Runs with python app.py (default http://127.0.0.1:8000)

## Coverage
Requirement coverage (URS 1.3)
FR01–FR13 are delivered; FR14–FR18 are declared Won't-have by the URS.
ID | Requirement | Status | Where / evidence
FR01 | HR can add a new employee record | Done | views.employee_create; TC-06
FR02 | HR can delete employee records | Done | views.employee_delete; TC-18/19
FR03 | HR can edit employee information | Done | views.employee_edit; TC-15
FR04 | Search an employee and open the detail view | Done | repositories.search_employees; TC-22
FR05 | Full overview list of all employees | Done | Home: Employee overview table; TC-21
FR06 | Supervisor plans the weekly rota (day + shift) | Done | views.employee_assign_shift; TC-31/32
FR07 | View one employee's weekly shifts / own timetable | Done | my_shifts.html, employee_detail.html; TC-41
FR08 | Full-store weekly rota for HR and Supervisor | Done | store_shifts.html; TC-38/54
FR09 | Supervisor reads employee data without edit rights | Done | RBAC + read-only pages; TC-29
FR10 | Only the Supervisor changes the rota | Done | route roles + tests; TC-44
FR11 | Human-readable validation errors | Done | htmlpages.validate_employee; TC-07
FR12 | Filter the employee list (wage, shift, sort) | Done | search_employees + filter bar; TC-25/26
FR13 | Workforce statistics | Done | KPIs, distribution table, statistics page; TC-58
FR14 | Department management | Won't-have | Out of scope per URS
FR15 | In-store attendance registration | Won't-have | Out of scope per URS
FR16 | Automatic shift generation | Won't-have | Out of scope per URS
FR17 | Product-stock / depot restock management | Won't-have | Out of scope per URS
FR18 | Employee self-service website | Won't-have | Out of scope per URS
NFR01 | Response time ≤ 2 s | Met | test_nonfunctional.py; 400+ employees
NFR02 | Role-based access control | Met | dispatcher + route roles; auth tests
NFR03 | Data persists after restart | Met | verify_persistence.py; SQLite file
NFR04 | User-friendly error handling | Met | error.html + validation; TC-14
NFR05 | 10 concurrent users | Met | concurrency tests; threaded server
NFR06 | Simple, usable interface | Met | shared layout, print styles, timetables

## Next Steps
What is left — ordered by priority
Only release/defence tasks remain; the feature iteration is delivered and pushed.
Priority | Card | Epic | Owner | Target | Definition of Done | Status
High | Update Acceptance Q&A (EN + bilingual) | Documentation | Spring | Before defence | Both documents describe the weekly rota, 137 tests and the current views | To Do
High | Copy URS 1.3 / Test Plan / Code Guide to the course folder | Delivery | Dylan | Before submission | All three documents present with the 1.3 / 1.1 versions | Busy
High | Demo rehearsal with the three accounts | Delivery | All | Day before defence | Login → home → rota → views → statistics → 403 demo all pass | Busy
Medium | Confirm the other-group test report is submitted | Delivery | Morty | Before submission | Report handed in (Project Plan deliverable) | To Do
Medium | Defence slides (finish / confirm) | Delivery | Jensen | Before defence | Slides follow the same storyline as the demo script | To Do
Low | Optional: tag release v1.1 + CHANGELOG | Delivery | Dylan | After submission | git tag pushed and listed on GitHub | To Do